## Employee Life Cycle
Question | Answer 1 | Answer 2 | Answer 3 | Answer 4 | Answer 5 | Multiple Answer | Right Answer
The role most accountable for project success is that of the: | A. Project sponsor. | B. Project owner. | C. Program manager. | D. Project manager. |  |  | 4
A project is best differentiated from a program in that: | A. A program is strategic whereas a project is tactical. | B. A project is unique to the organization whereas a program may be identical to other programs. | C. A program is managed by a senior manager whereas a project is managed by a project manager. | D. A project is time-limited whereas programs may not be. |  |  | 4
A baseline is best described as: | A. The measurement standard for project performance estimations. | B. The product owners initial product backlog before any grooming. | C. The original plan plus all approved changes. | D. Thee criteria to which the project sponsor holds the project manager accountable. |  |  | 3
The project sponsor’s primary role is to: | A. Pay for the project. | B. Approve the deliverables. | C. Be the Voice of the Customer. | D. Organize the stakeholders. |  |  | 1
The project charter is: | A. The initial project plan until the formal one is developed. | B. Signed by the project manager. | C. Symbolic only with no real authorization properties. | D. The project’s first official project document. |  |  | 4
What processes include defining and authorizing a project or project phase? | A. Initiating | B. Planning | C. Executing | D. Monitoring and controlling |  |  | 1
What is the main purpose of project plans? | A. schedule management plans | B. define project scope | C. estimate activity resources | D. guide project execution |  |  | 4
Which is true about the agile method? | A. It is often used when a project team can express the scope early in the product life cycle. | B. It is used when a project team wants to provide a potentially shippable product earlier rather than later. | C. It uses several iterations or deliveries of software instead of waiting until the end of the project to provide a product | D. It is used when project teams want to use the predicative approach to a project. |  |  | 3
In the Scrum method, during which meeting is the improvement of the product and process discussed? | A. sprint retrospective | B. sprint review | C. kick-off | D. daily Scrum |  |  | 1
Which planning process is associated with project scope management? | A. Collecting requirements | B. Performing qualitative risk analysis | C. Planning schedule management | D. Estimating costs |  |  | 1
What statement is true regarding a return on investment or ROI? | A. It is always a percentage. | B. It is always a positive number. | C. It is the result of adding the project costs to the profits. | D. The lower it is, the better. |  |  | 1
An IT company revises its process parameters in response to complaints from vendors that products were not ready on time. Which is this an example of? | A. cost forecasting | B. a preventive action | C. defect repairs | D. a corrective action |  |  | 4
During which approach do team members first identify as many specific tasks related to the project as possible and then aggregate the specific tasks and organize them into summary activities, or higher levels in the WBS? | A. Analogy | B. bottom-up | C. top-down | D. mind mapping |  |  | 2
Which is recommended for the creation of a good WBS? | A. Any WBS item should be the responsibility of all the people working on it. | B. A unit of work should appear at only one place in the WBS. | C. Each WBS item should be created assuming that the requirements are inflexible. | D. The work content of a WBS item is independent of the WBS items below it. |  |  | 2
What process group does the project integration management knowledge area map to through the activities of developing project charters? | A. Initiating | B. Planning | C. Executing | D. monitoring and controlling |  |  | 1
Which action involves defining and documenting the features and functions of the products produced during the project as well as the processes used for creating them? | A. Collecting requirements | B. Defining scope | C. Controlling scope | D. Validating scope |  |  | 1
Which document contains a deliverable-oriented grouping of the work involved in a project that defines the total scope of the project? | A. project charter | B. business case | C. project scope statement | D. work breakdown structure |  |  | 4
Which approach for constructing a WBS uses a similar project’s WBS as a starting point? | A. top-down | B. bottom-up | C. mind-mapping | D. analogy |  |  | 4
What is the first step in the planning process? | A. tie the information technology strategic plan to the organization’s overall strategic plan | B. perform a business area analysis | C. start defining potential IT projects in terms of their scope, benefits, and constraints | D. choose which projects to do and assigning resources to work on them |  |  | 1
What type of analysis involves calculating the expected net monetary gain or loss from a project by discounting all expected future cash inflows and outflows to the present point in time? | A. Cost of capital | B. Net present value | C. Cash flow | D. Payback |  |  | 2
What term is used for the minimum acceptable rate of return on an investment? | A. capitalization rate. | B. internal rate of return | C. discount rate | D. required rate of return |  |  | 4
When does payback occur? | A. When the net cumulative benefits minus costs equal one | B. When the net cumulative benefits equal the net cumulative costs | C. When the net costs are lower than the cumulative benefits | D. When the cumulative benefits are double the cumulative costs |  |  | 2
The project cost management knowledge area maps to which process group through the activities of estimating costs and budget determination? | a. initiating | b. planning | c. executing | d. monitoring and controlling |  |  | 2
24. Reporting performance, where project stakeholders can identify any necessary changes that may be required to keep the project on track, is a common part of which process? | A. executing | B. closing | C. monitoring and controlling | D. planning |  |  | 3
Which processes include acquiring and developing the project team, performing quality assurance, distributing information, managing stakeholder expectations, and conducting procurements? | A. monitoring and controlling | B. executing | C. planning | D. initiating |  |  | 2
A project’s internal rate of return can be determined by finding what discount rate results in an NPV of what value for the project? | A. Zero | B. One | C. A hundred percent | D. Fifty percent. |  |  | 1
Which action involves normalizing acceptance of the project deliverables and during this phase the key project stakeholders, such as the customer and sponsor for the project, inspect and then formally accept the deliverables? | A. Creating scope | B. Defining scope | C. Controlling scope | D. Validating scope |  |  | 4
What processes include devising and maintaining a workable scheme to ensure that the project addresses the organization’s needs? | A. Initiating | B. Planning | C. Executing | D. Monitoring and controlling |  |  | 2
The project schedule management knowledge area maps to which process group through the activity of schedule control? | A. initiating | B. planning | C. executing | D. monitoring and controlling |  |  | 4
Which process involves gaining stakeholder and customer acceptance of the final products and services and bringing the project, or project phase, to an orderly end? | A. executing | B. closing | C. planning | D. monitoring |  |  | 2

## Sheet2
Yes
No