Q1:

| Activity | a | m | b | predecessors |
| --- | --- | --- | --- | --- |
| a | 1 | 4 | 7 |  |
| b | 2 | 2 | 2 |  |
| c | 2 | 5 | 8 | a |
| d | 3 | 4 | 5 | a |
| e | 4 | 6 | 8 | c, b |
| f | 0 | 0 | 6 | c, b |
| g | 3 | 6 | 9 | d, e |

Find

- The network.

- All expected activity time , variances and slack

- Critical path and expected completion time

- The probability the project will be done in 23 days.

- The completion time corresponding to 95% probability.

Q2:

Given the following information, draw the AON diagram

| Activity | Immediate predecessor |
| --- | --- |
| 1 |  |
| 2 |  |
| 3 | 1,4 |
| 4 | 2 |
| 5 | 2 |
| 6 | 3,4 |

Q3: Given the information below, create the project schedule network. Then, using the two-pass method , calculate and show the early and late start and float for each activity and the critical path.

| Activity | Days | Immediate Predecessor |
| --- | --- | --- |
| A | 5 |  |
| B | 2 | A |
| C | 4 | A |
| D | 7 | A |
| E | 3 | B |
| F | 6 | B, C |
| G | 8 | D, E,F |