Critical Chain Project Management

- The activities precedence relationship and resource requirement of a project are given as below. This project has six persons to perform all activities and the assignment of the resources is shown in the table.

| Activities | Predecessor | Time | Resource requirement |
| --- | --- | --- | --- |
| A | ---- | 2 | Ryan |
| B | A | 15 | Carly |
| C | A | 18 | Ryan |
| D | A | 13 | Laurn |
| E | A | 18 | Connor |
| F | D | 15 | Ryan |
| G | B,C,F | 10 | Dawn |
| H | E,G | 5 | Kevin |

Develop the critical chain for the above network. Insert feeder buffer, and project buffer and determine the project completion time.

- Consider the project network given below. Develop a criticla chain for the given network.

- Consider the data about project activities given in the table below. Develop the critical chain and indicate the feeder buffer and project buffer in the critical chain.

| Activity | Predecessor | Duration | Resources |
| --- | --- | --- | --- |
| A | -- | 2 | Engineer |
| B | A | 3 | Marketing |
| C | -- | 3 | Engineer, Marketing |
| D | C | 2 | Finance |
| E | D,J | 3 | Marketing, Finance |
| F | E,B | 2 | Engineer |
| G | F | 2 | Production |
| H | -- | 4 | Marketing |
| J | H | 2 | Finance |

Assume the size of feeder buffer, and project buffer as 50% length of non-critical path and critical chain respectively.

- Given the following information’s, compute early, late and slack times for the project network.

| ID | Duration | Finish-to-start Predecessor | Finish-to-start Lag | Additional Lag relationship | Lag |
| --- | --- | --- | --- | --- | --- |
| A | 2 | None | 0 | None | 0 |
| B | 4 | A | 0 | None | 0 |
| C | 6 | A | 0 | Finish-Finish C to F | 7 |
| D | 8 | A | 0 | None | 0 |
| E | 18 | B | 0 | Finish-Finish E to G | 9 |
|  |  | C | 10 |  |  |
| F | 2 | D | 0 | None |  |
| G | 5 | F | 0 | Start-start G to H | 10 |
| H | 5 | None | 0 | None | 0 |
| I | 14 | E | 0 | Finish-Finish I to J | 5 |
| J | 15 | G, H | 0 | None | 0 |