## Sheet1
Task | Description | Most optimistic | Most likely | Most pessimistic | IP |  | Normal time | Variance | Earliest start time | Earliest finish time | Latest start time | Latest finish time | Slack |  |  | Normal time (expected) = (Most optimistic time + 4* Most likely time + Most pessimistic time)/6
A |  | 2 | 3 | 4 | - |  | 3 | 0.11111 | 0 | 3 | 0 | 3 | 0 |  | 7.16 | Variance = (Most pessimistic time - Most optimistic time)^2/36
B |  | 4 | 7 | 10 | A |  | 7 | 1 | 3 | 10 | 19.5 | 26.5 | 16.5 |  |  | The level of volatility of the time required to carry an activity from the average time
C |  | 5 | 6 | 9 | A |  | 6.3333 | 0.44444 | 3 | 9.3333 | 2.9967 | 9.33 | -0.0033333
D |  | 6 | 7 | 16 | C |  | 8.3333 | 2.7778 | 9.3333 | 17.6667 | 9.3367 | 17.67 | 0.0033333 |  |  | Total slack is calculated as the smaller value of the Late Finish minus the Early Finish field, and the Late Start minus the Early Start field.
E |  | 7 | 9 | 10 | D |  | 8.8333 | 0.25 | 17.6667 | 26.5 | 17.6667 | 26.5 | 0 |  |  | Slack time is the amount of time a task can delay without delaying the project deadline
F |  | 4 | 5 | 6 | B,E |  | 5 | 0.11111 | 26.5 | 31.5 | 26.5 | 31.5 | 0
G |  | 3 | 6 | 10 | D |  | 6.1667 | 1.3611 | 17.67 | 23.8367 | 25.3333 | 31.5 | 7.6633 |  |  | Critical path - ACDEFJK
H |  | 2 | 4 | 7 | C,E |  | 4.1667 | 0.69444 | 26.5 | 30.6667 | 27.3333 | 31.5 | 0.83333
I |  | 2 | 2 | 2 | B |  | 2 | 0 | 10 | 12 | 29.5 | 31.5 | 19.5
J |  | 3 | 4 | 14 | F,G,H,I |  | 5.5 | 3.3611 | 31.5 | 37 | 31.5 | 37 | 0
K |  | 2 | 3 | 4 | J |  | 3 | 0.11111 | 37 | 40 | 37 | 40 | 0
40
Task | Normal time | Normal Cost | Crash Time | Crash Cost | Normal time-crash time | Extra | Latest finish time |  | Expected | 40
A | 3 | 10000 | 3 | 10000 | 0 | 0 | 3 | C | Minimum | 33 weeks is minimum completion time |  | To determine probability that project can be completed in 35 weeks, we need to know the variance of the project. The variance of the project is the sum of variances of the activities that are on critical path
B | 7 | 20000 | 6 | 25000 | 1 | 5000 | 26.5 |  |  |  |  | The variance of critical path is 7.2 weeks
C | 6.3333 | 15000 | 5 | 30000 | 1.3333 | 15000 | 9.33 | C
D | 8.3333 | 45000 | 6 | 65000 | 2.3333 | 20000 | 17.67 | C |  | 7.1667 |  |  | Variance | 7.2 | 2.6833
E | 8.8333 | 10000 | 8 | 20000 | 0.83333 | 10000 | 26.5 | C |  | Variance of critical pat | 7 weeks |  | SQRT | 2.68
F | 5 | 15000 | 4 | 18000 | 1 | 3000 | 31.5 | C |  |  |  |  | DEADLINE | 35
G | 6.1667 | 20000 | 4 | 30000 | 2.1667 | 10000 | 31.5 | [5 empty] | EXPECTED COMPLETION | 40
H | 4.1667 | 10000 | 3 | 15000 | 1.1667 | 5000 | 31.5
I | 2 | 5000 | 2 | 5000 | 0 | 0 | 31.5 |  |  |  | 35 | 0.031204 |  | 0.031044 | 3.01 Percent proabability that project can be completed in 35 weeks
J | 5.5 | 40000 | 5 | 50000 | 0.5 | 10000 | 37 | C
K | 3 | 15000 | 2 | 25000 | 1 | 10000 | 40 | C |  |  | 40 | 0.0045015

## Sheet2
Task | Normal time | Crash Time | Crash Cost | Maximum crash days Normal time - crash time |  | 35
A | 3 | 3 | 10000 | 0 | 0
C | 6.3333 | 5 | 30000 | 1.3333 | 1
D | 8.3333 | 6 | 65000 | 2.3333 | 1
E | 8.8333 | 8 | 20000 | 0.83333 | 1
F | 5 | 4 | 18000 | 1 | 0
J | 5.5 | 5 | 50000 | 0.5 | 1 |  | crash days | Crash cost
K | 3 | 2 | 25000 | 1 | 0 |  | 7 | 218000
[7 empty] | 5.16 | 128000
[7 empty] | 5 | 165000
|  |  | 165000 | 5