- For a given project, activity their predecessor, labor requirement and material cost (in $) is given in the following table. The rate of resources for marketing, finance and engineering is as $100, $120 and $180 per hour respectively. Assume 5 days working week. The project would start from 1 January 2018.

| Activity | Predecessor | Time (days) | Material cost in $ | Labor Requirement |
| --- | --- | --- | --- | --- |
| H | - | 10 | 100 | 2M, 1F, 2E |
| I | H | 8 | 64 | 1M, 1F, 1E |
| J | H | 6 | 96 | 1M, 2F, 3E |
| K | J | 4 | 16 | 2M, 2F, 2E |
| L | J | 2 | 36 | 1M, 2F, 2E |
| M | J | 4 | 84 | 2M, 2F, 2E |
| N | I | 4 | 80 | 3M, 1F, 4E |
| O | I | 5 | 50 | 2M, 2F, 3E |
| P | J | 5 | 60 | 3M, 4F, 2E |
| Q | L | 5 | 80 | 4M, 2F, 2E |
| R | M | 5 | 10 | 2M, 2F, 2E |
| S | N | 3 | 10 | 3M, 1F, 1E |
| T | Q | 3 | 10 | 1M, 3F, 3E |
| U | O, S | 1 | 14 | 1M, 1F, 1E |
| V | K, R | 5 | 80 | 3M, 3F, 3E |
| W | U | 2 | 24 | 1M, 2F, 2E |
| X | V | 3 | 36 | 1M, 3F, 3E |
| Y | P,W,X | 8 | 104 | 2M, 3F, 1E |
| Z | T,Y | 6 | 66 | 3M, 1F, 3E |

PART A:  What is the completion date of the project and how many working days are required to complete this project? If you have 10 resources form each department.

PART B:  What is the completion date of the project and how many working days are required to complete this project? If you have 5 resources form each department.

- A consulting firm implement the project with the following data. Assume labor rate $ 400 per month. The project start date is 29 October 2018 and there is 5 days working week. Holidays are observed on Nov 7 & 8, December 25, September 03, March 1 & 30 October 18.

| Activity |  | Duration (Months) | Fixed Cost (Thousands $) | Labor Requirement (worker months) |
| --- | --- | --- | --- | --- |
| A | 1-2 | 4 | 8 | 4 |
| B | 1-3 | 3 | 9 | 4 |
| C | 2-3 | 2 | 10 | 5 |
| D | 2-4 | 4 | 12 | 6 |
| E | 3-4 | 5 | 15 | 7 |
| F | 3-5 | 6 | 12 | 6 |
| G | 4-5 | 1 | 10 | 5 |

(a) Construct weekly expenses chart and cumulative expenses chart

(b) Compare the pattern of expenditure for both an early start schedule and a late start schedule.