## Slide 1
PROJECT CHARTER TEMPLATE WITH EXAMPLE DATA
IMPORTANT REMINDER
A narrative written charter must be circulated and signed by the project sponsors. You can attach a completed version of this template to your narrative written charter in an effort to keep it short and concise.
Please make sure you meet with the project team and sponsors before completing this template. Much of the information required will need to come from a discussion with team members and sponsors.

## Slide 2
PROJECT CHARTER | GENERAL PROJECT INFORMATION
 | PROJECT NAME |  |  | PROJECT MANAGER | PROJECT SPONSOR
 | EV Charge Station Installations |  |  | Mr. A | Mr. B
 | EMAIL |  | PHONE | ORGANIZATIONAL UNIT | 
 | 123@gmail.com |  | 000-000-0000 | Field Engineering, Operations, and Project Management | 
 |  |  |  | EXPECTED START DATE | EXPECTED COMPLETION DATE
 |  |  |  | 2/19/20XX | 11/30/20XX
 |  |  |  | EXPECTED SAVINGS | ESTIMATED COSTS
 |  |  |  | $237,750 | $441,885
GENERAL PROJECT INFORMATION

## Slide 3
TABLE OF CONTENTS
PROJECT OVERVIEW & PROJECT SCOPE
TENTATIVE SCHEDULE
2
3
1
RESOURCES & COSTS
RISK, CONSTRAINTS, & ASSUMPTIONS
PREPARED BY…
6
5
4
BENEFITS & CUSTOMERS

## Slide 4
PROJECT REPORT
1. PROJECT OVERVIEW
PROJECT SCOPE
PROBLEM OR ISSUE | Our goal for this project is to install EV charging stations at 116 locations across India to accommodate needs of EV users.
PURPOSE OF PROJECT | The implementation of the EV charging stations will reduce fossil-fuel emissions and have a positive impact on the environment. This will help fulfill Positive Charge's mission of being the world's largest EV-charging provider and reduce the environmental impact of fossil-fuel cars through our services.
BUSINESS CASE | As EVs become more prevalent, more EV-charging stations are needed to accommodate EV drivers' charging needs. The implementation of the EV charging stations at 116 locations across the India to accommodate needs of EV users and service stations' EV-charging "traffic" will reduce the lengths to which EV drivers would have to travel for their next charge. The implementation of the EV-charging stations will also result in a 24% profit for Positive Charge.
GOALS / METRICS | The project goal is to install EV charging stations at 116 locations across the India. The metrics used to measure success will primarily be the following key performance indicators (KPIs): Revenue Growth, Client Retention Rate, and Customer Satisfaction.
EXPECTED DELIVERABLES | Install EV charging stations at 116 locations across the India to accommodate the needs of beneficiaries
WITHIN SCOPE | Operations engineers, project managers and field implementation engineers will work with third-party client site personnel to install EV charging stations at 116 locations across the India.
OUTSIDE OF SCOPE | Positive Charge is not responsible for third-party / client's locations preparatory work (e.g., permits for digging, city region electricity-availability logistics, etc.). However, Positive Charge project managers can provide clients with a checklist to ensure their locations are adequately prepared for the installation of our EV charging stations.

## Slide 5
PROJECT REPORT
2. TENTATIVE SCHEDULE
KEY MILESTONE | START | FINISH
Form Project Team / Preliminary Review / Scope | 12/05/20XX | 01/11/20XX
Finalize Project Plan / Charter / Kick Off | 12/06/20XX | 02/01/20XX
Define Phase | 12/07/20XX | 02/02/20XX
Measurement Phase | 12/08/20XX | 02/10/20XX
Analysis Phase | 12/09/20XX | 02/26/20XX
Improvement Phase | 01/10/20XX | 03/10/20XX
Control Phase | 02/08/20XX | 03/08/20XX
Project Summary Report and Close Out | 04/23/20XX | 06/23/20XX

## Slide 6
3. RESOURCES
PROJECT TEAM | Team |  | 
SUPPORT RESOURCES | Operations, Sales, Project Management, Engineering |  | 
SPECIAL NEEDS | TBD |  | 
COSTS
COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT
Labor | Electro Charge Logistics, Inc. |  | $78.00 | 200 | $ 15,600.00
Labor | Level 1 EVS |  | $46.00 | 100 | $ 4,600.00
Labor | Level 2 EVS |  | $58.00 | 50 | $ 2,900.00
Labor | EVC Fast Chargers |  | $85,000.00 | 1 | $ 85,000.00
Labor | Battery Vendor |  | $79,879.00 | 3 | $ 239,637.00
Supplies | Power Conversion System Vendor |  | $68,686.00 | 1 | $ 68,686.00
Miscellaneous | Third-Party Software |  | $25,432.00 | 1 | $ 25,432.00
 |  |  | TOTAL COSTS |  | $ 441,855.00

## Slide 7
PROJECT REPORT
4. BENEFITS & CUSTOMERS
PROCESS OWNER | ABC
KEY STAKEHOLDERS | XYZ
FINAL CUSTOMER | 116 clients across the India
EXPECTED BENEFITS | The implementation of the EV charging stations at 116 locations across the India to accommodate needs of EV users and service stations' EV-charging "traffic" will reduce the lengths to which EV drivers would have to travel for their next charge. The implementation of the EV-charging stations will also result in a 24% profit for Positive Charge.
TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  | ESTIMATED BENEFIT AMOUNT
Specific Cost Savings | Estimator's projections |  |  | $ 25,000.00
Enhanced Revenues | Finance's projections |  |  | $ 92,500.00
Higher Productivity (Soft) | Project management's estimations |  |  | $ 17,500.00
Improved Compliance | Operations' estimations |  |  | $ 12,000.00
Better Decision Making | Project management's estimations |  |  | $ 18,500.00
Less Maintenance | Project management's estimations |  |  | $ 26,000.00
Other Costs Avoided | Finance's projections |  |  | $ 46,250.00
 |  |  | TOTAL BENEFIT | $ 237,750.00

## Slide 8
PROJECT REPORT
5. RISKS, CONSTRAINTS & ASSUMPTIONS
RISKS | Though contract is signed, Operations still does not have approval for installation from cities of Jammu, Himachal & Punjab. Project management to work with both cities to ensure proper permitting, etc. in time for scheduled installations.
CONSTRAINTS | We have to "backfill" some key project management and field engineer positions to ensure we have people "on the ground" to manage EV stations' implementation.
ASSUMPTIONS | We assume that all permits for installation of EV-charging stations will be provided by clients by time of implementation.

## Slide 9
PREPARED BY | TITLE | DATE
Mr. E | Senior Project Manager | 04/22/20XX
6. PREPARED BY