## CheckList
Performance
Project | Criteria | High | Medium | Low
Janus | Stategic fit |  | (×)
| Prbability of technical success |  | (×)
| Fiancial risk |  |  | (×)
| Poential profit | (×)
| Stategic leverage |  |  | (×)
Gemini | Stategic fit | (×)
| Prbability of technical success |  | (×)
| Fiancial risk |  | (×)
| Poential profit | (×)
| Stategic leverage |  | (×)

## AHP
Step 1: |  | Step 2:
First level | Second level
1. Financial benefits (0.52) | 1A: Short-term (0.156) | [19 empty] | FB | 36
| 1B: Long-term (0.364) | FB | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | CS | CS | 7
2. Contribution to strategy (0.34) | 2A: Increasing market share for product X; (0.1020) | FB | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | IT | IT | 3
| 2B: Retaining existing customers for product Y; (0.1564) | CS | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | IT | FB weight | 0.78261
| 2C: Improving cost management (0.0816) | [19 empty] | CS weight | 0.15217
3. Contribution to IT infrastructure (0.140) |  | FB | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | CS | IT weight | 0.065217
|  | FB | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | IT
60 | 30 | CS | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | IT | Total | 1
30 | 70
10 | 0.18 | FB | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | CS
0.6 | 0.42 | FB | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | IT | [5 empty] | Step 4:
0.3 |  | CS | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | IT | Step 3: |  |  |  |  | 1. Financial benefits (0.52) |  | 2. Contribution to strategy (0.34) |  |  | 3. Contribution to IT infrastructure (0.140)
0.1 | [20 empty] | Evaluation Dimention | Numerical Value | Priority | Nominal Value |  | 1A: Short-term (0.156) | 1B: Long-term (0.364) | 2A: Increasing market share for product X; (0.1020) | 2B: Retaining existing customers for product Y; (0.1564) | 2C: Improving cost management (0.0816) |  | Total
[21 empty] | Poor | 0 | 0 | 0 |  | 0.156 | 0.364 | 0.102 | 0.1564 | 0.0816 | 0.14 | 1
[21 empty] | Fair | 10 | 0.05 | 0.1 | A | Excellent | Excellent | Excellent | Excellent | Excellent | Excellent | 1
[21 empty] | Good | 30 | 0.15 | 0.3 | B | Good | Excellent | Good | Excellent | Good | Excellent | 0.76228
[21 empty] | Very Good | 60 | 0.3 | 0.6 | C | Excellent | Good | Excellent | Good | Excellent | Good | 0.53772
[21 empty] | Excellent | 100 | 0.5 | 1 | D | Very Good | Very Good | Very Good | Very Good | Very Good | Very Good | 0.6
Step 1: | [22 empty] | 1 | 2 | E | Poor | Fair | Good | Very Good | Excellent | Good | 0.28444
First level | Second level
1. Financial benefits (0.52) | 1A: Short-term (0.156)
1B: Long-term (0.364)
2. Improvement of Customer Experience | [25 empty] | 0.156 | 0.364 | 0.102 | 0.1564 | 0.0816 | 0.14 | 1
[26 empty] | 0.0468 | 0.364 | 0.0306 | 0.1564 | 0.02448 | 0.14 | 0.76228
[26 empty] | 0.156 | 0.1092 | 0.102 | 0.04692 | 0.0816 | 0.042 | 0.53772
[26 empty] | 0.0936 | 0.2184 | 0.0612 | 0.09384 | 0.04896 | 0.084 | 0.6
[26 empty] | 0 | 0.0364 | 0.0306 | 0.09384 | 0.0816 | 0.042 | 0.28444

## PB
Year | Cash Flow | Cumulative
0 | -200000 | -200000
1 | 75000 | -125000
2 | 75000 | -50000
3 | 75000 | 25000
2.6667

## Case - PB
Janus |  |  | Gemini
Year | Net flow | Cum | Year | Net flow | Cum
0 | -250000 | -250000 | 0 | -400000 | -400000
1 | 50000 | -200000 | 1 | 75000 | -325000
2 | 100000 | -100000 | 2 | 250000 | -75000
3 | 100000 | 0 | 3 | 300000 | 225000
4 | 200000 | 200000
5 | 75000 | 275000
|  | 3 |  |  | 2.25
|  | Payback period |  |  | Payback period

## TVOM
Time value of Money
13513.5136 | 0.11 | 15000.0001
0.9009 | 0.11 | 1
8901.77

## NPV
Manual
| Inflation | 0.03
| RR | 0.08
Year | Net flow | Discount | NPV
0 | -60000 | 1 | -60000
1 | 15000 | 0.9009 | 13513.5135
2 | 15000 | 0.81162 | 12174.3365
3 | 15000 | 0.73119 | 10967.8707
4 | 15000 | 0.65873 | 9880.9646
5 | 15000 | 0.59345 | 8901.7699
-4561.5447

## NPV2
Manual |  |  |  | Excel
| Inflation | 0.03 |  | 0.11
| RR | 0.08
Year | Net flow | Discount | NPV
0 | -60000 | 1 | -60000
1 | 15000 | 0.9009 | 13513.5135
2 | 15000 | 0.81162 | 12174.3365
3 | 15000 | 0.73119 | 10967.8707
4 | 15000 | 0.65873 | 9880.9646
5 | 15000 | 0.59345 | 8901.7699
|  |  | -4561.5447 | -4561.5447

## Case - NPV
Manual |  |  |  | Manual
| RR | 0.15 |  |  | RR | 0.15
| Inflation | 0.03 |  |  | Inflation | 0.03
Year | Net flow | Discount | NPV | Year | Net flow | Discount | NPV
0 | -250000 | 1 | -250000 | 0 | -400000 | 1 | -400000
1 | 50000 | 0.84746 | 42372.8814 | 1 | 75000 | 0.84746 | 63559.322
2 | 100000 | 0.71818 | 71818.443 | 2 | 250000 | 0.71818 | 179546.1074
3 | 100000 | 0.60863 | 60863.0873 | 3 | 300000 | 0.60863 | 182589.2618
4 | 200000 | 0.51579 | 103157.775
5 | 75000 | 0.43711 | 32783.1912
|  |  | 60995.3778 |  |  |  | 25694.6913

## Case - DPB
| Manual | [5 empty] | Manual
|  | Inflation | 0.15 |  |  |  |  | Inflation | 0.15
Janus |  | RR | 0.03 |  |  | Gemini |  | RR | 0.03
| Year | Net flow | Discount | NPV | Cum |  | Year | Net flow | Discount | NPV | Cum
| 0 | -250000 | 1 | -250000 | -250000 |  | 0 | -400000 | 1 | -400000 | -400000
| 1 | 50000 | 0.84746 | 42372.8814 | -207627.1186 |  | 1 | 75000 | 0.84746 | 63559.322 | -336440.678
| 2 | 100000 | 0.71818 | 71818.443 | -135808.6757 |  | 2 | 250000 | 0.71818 | 179546.1074 | -156894.5705
| 3 | 100000 | 0.60863 | 60863.0873 | -74945.5884 |  | 3 | 300000 | 0.60863 | 182589.2618 | 25694.6913
| 4 | 200000 | 0.51579 | 103157.775 | 28212.1866
| 5 | 75000 | 0.43711 | 32783.1912 | 60995.3778
|  |  |  | 60995.3778 | 3.7265 |  |  |  |  | 25694.6913 | 2.8593
[5 empty] | Disocunted Payback period | [5 empty] | Disocunted Payback period

## Solver
Project Budget | 70000
Total Selected Project Cost | 60000
Surplus/Overrun | 10000
Total NPV | 55000
Project | Project Cost | NPV | Selected
1 | 15000 | 14000 | 1
2 | 61000 | 17000 | 0
3 | 12000 | 17000 | 1
4 | 8000 | 15000 | 0 | 4 |  | 5
5 | 67000 | 40000 | 0 | 0 | <= | 0,1 | If 4 is taken, 5 must be taken.
6 | 12000 | 12000 | 1 | 1 | <= | 1 | 4 should be taken
7 | 52000 | 14000 | 0 |  |  |  | only 3 projects should be taken
8 | 39000 | 10000 | 0
9 | 21000 | 12000 | 1