Project Resourcing: Managing resource conflicts, Trade-off between penalty cost vs resource cost by MS Project software

- A project has the following time and resource data:

| Activity | Predecessor | Duration | Labor requirement |
| --- | --- | --- | --- |
| A | None | 2 | 4 |
| B | A | 3 | 3 |
| C | A | 4 | 3 |
| D | B | 2 | 5 |
| E | D | 6 | 3 |
| F | C | 4 | 3 |
| G | C | 3 | 4 |
| H | F | 6 | 6 |
| I | G | 3 | 2 |
| J | E, H | 4 | 2 |
| K | I | 4 | 9 |

PART A: Find the project schedule if only 11 men are available

PART B: Find the project schedule if only 9 men are available

- Develop the project schedule of the given project when only 4 men are available to perform the activities and determine how many days are required to complete the project.

| Activity | Predecessor | Duration | Labor requirement |
| --- | --- | --- | --- |
| A | None | 10 | 1 |
| B | None | 6 | 2 |
| C | None | 5 | 3 |
| E | A | 8 | 1 |
| F | B | 10 | 2 |
| G | F | 10 | 3 |
| H | C | 7 | 1 |
| I | E | 5 | 2 |

PART B: How many resources are required to complete the project in 26 days?

- A project has the following time and resource data. How many men are required to complete the project in 15 days?

| Activity | Predecessor | Duration | Labor Requirement |
| --- | --- | --- | --- |
| A | None | 5 | 1 |
| B | None | 3 | 1 |
| C | None | 2 | 1 |
| E | A | 4 | 1 |
| F | B | 5 | 1 |
| G | F | 5 | 1 |
| H | C | 3 | 1 |
| I | E | 3 | 1 |

- For a given project, activity their predecessor, labor requirement and material cost (in $) is given in the following table. The rate of resources for marketing, finance and engineering is as $100, $120 and $180 per hour respectively. Assume 5 days working week. The project would start from 6 January 2020.

The following holidays are observed: January 15, February 18, March 10, April 14, and May 07.

| Activity | Predecessor | Time (days) | Material cost in $ | Labor Requirement |
| --- | --- | --- | --- | --- |
| H | - | 10 | 100 | 2M, 1F, 2E |
| I | H | 8 | 64 | 1M, 1F, 1E |
| J | H | 6 | 96 | 1M, 2F, 3E |
| K | J | 4 | 16 | 2M, 2F, 2E |
| L | J | 2 | 36 | 1M, 2F, 2E |
| M | J | 4 | 84 | 2M, 2F, 2E |
| N | I | 4 | 80 | 3M, 1F, 4E |
| O | I | 5 | 50 | 2M, 2F, 3E |
| P | J | 5 | 60 | 3M, 4F, 2E |
| Q | L | 5 | 80 | 4M, 2F, 2E |
| R | M | 5 | 10 | 2M, 2F, 2E |
| S | N | 3 | 10 | 3M, 1F, 1E |
| T | Q | 3 | 10 | 1M, 3F, 3E |
| U | O, S | 1 | 14 | 1M, 1F, 1E |
| V | K, R | 5 | 80 | 3M, 3F, 3E |
| W | U | 2 | 24 | 1M, 2F, 2E |
| X | V | 3 | 36 | 1M, 3F, 3E |
| Y | P,W,X | 8 | 104 | 2M, 3F, 1E |
| Z | T,Y | 6 | 66 | 3M, 1F, 3E |

PART A:  What is the completion date of the project and how many working days are required to complete this project? If you have 10 resources form each department.

PART B:  What is the completion date of the project and how many working days are required to complete this project? If you have 5 resources form each department.