## Sheet2
| Activity Name | Activity | Predesessor | Optimistic | Most likely | Pessimistic | Crash cost/day | Expected Value | Variance | Early Start | Early Finish | Late start | Late finish | Slack | Expected Value (250 Days) | Expected Value (250 Days)
1 | Bonding, Insurance, tax structuring | A |  | 20 | 30 | 40 | 1500 | 30 | 11.1111 | 0 | 30 | 0 | 30 | 0 | 20 | 20
2 | Foundation, concrete footings for boxes | B | A | 20 | 65 | 80 | 3500 | 60 | 100 | 30 | 90 | 59.9 | 119.9 | 29.9 | 60 | 60
3 | Upgrading skybox stadium seating | C | A | 50 | 60 | 100 | 4000 | 65 | 69.4444 | 30 | 95 | 30 | 95 | 0 | 65 | 65
4 | Upgrading walkways, stairwells, elevators | D | C | 30 | 50 | 100 | 1900 | 55 | 136.1111 | 95 | 150 | 95 | 150 | 0 | 55 | 45
5 | Interior wiring, Lathes | E | B | 25 | 30 | 35 | 9500 | 30 | 2.7778 | 90 | 120 | 119.9 | 149.9 | 29.9 | 30 | 30
6 | Inspection approvals | F | E | 0.1 | 0.1 | 0.1 | 0 | 0.1 | 0 | 120 | 120.1 | 149.9 | 150 | 29.9 | 0.1 | 0.1
7 | Plumbing | G | D, F | 25 | 30 | 35 | 2500 | 30 | 2.7778 | 150 | 180 | 150 | 180 | 0 | 30 | 30
8 | Painting | H | G | 10 | 20 | 30 | 2000 | 20 | 11.1111 | 180 | 200 | 180 | 200 | 0 | 20 | 20
9 | Hardware/AC/metal workings | I | H | 20 | 25 | 60 | 2000 | 30 | 44.4444 | 200 | 230 | 200 | 230 | 0 | 30 | 30
10 | Tile/carpet/windows | J | H | 8 | 10 | 12 | 6000 | 10 | 0.44444 | 200 | 210 | 219.9 | 229.9 | 19.9 | 10 | 10
11 | Inspection | K | J | 0.1 | 0.1 | 0.1 | 0 | 0.1 | 0 | 210 | 210.1 | 229.9 | 230 | 19.9 | 0.1 | 0.1
12 | Final detail work/cleanup | L | I, K | 20 | 25 | 60 | 4500 | 30 | 44.4444 | 230 | 260 | 230 | 260 | 0 | 30 | 30
[7 empty] | Length of critical path | 260
[7 empty] | Variance | 319.4444
[7 empty] | Deviation | 17.873
[7 empty] | Expected Duration | 327.2025
[7 empty] | Prob(270) | 71.2091
[7 empty] | Crashing from 260 to 250 days | 15000
[7 empty] | Crashing from 250 to 240 days | 19000
[7 empty] | Total Crashing Cost | 34000