The Cable Contract (Remaining Facts)

After signing the contract, Chandran realised that it will be good if he can compute the risk of his project. Though he had no clue about such big Government project, he had some idea about small sub-contracting works. He reviewed the network diagram of the project (figure given below) and based on his experience and intuition, he estimated the most pessimistic time, optimistic time and most likely time of completion of each activity in the Cable contract job. Based on the risk analysis, determine the most likely time of project completion and the probability of finishing the job in 21 days?

Start

Cable Procurement

Excavation

Cable laying

Trench covering

Connection

| Activity | Predecessor | Time Estimate |  |  |
| --- | --- | --- | --- | --- |
|  |  | Optimistic | Likeliest | Pessimistic |
| Start |  | 1 | 2 | 4 |
| Excavation | Start | 1 | 3 | 7 |
| Cable procurement | Start | 1 | 1 | 1 |
| Cable Laying | Cable procurement, Excavation | 2 | 4 | 6 |
| Trench covering | Cable Laying | 2 | 4 | 6 |
| Connection | Trench covering | 2 | 5 | 7 |