## WBS
| Colour Scheme | Legends
| Completed | HG - Harshit Garg
| Estimated | AZ- Abuzaid Ansari
| Mid term Exams | SA- Suyash Agrawal
DG- Divya Giri
RO- Rohit
|  | TK - Tanvi Karguppikar |  | Months
|  |  |  | June | [15 empty] | July | [30 empty] | August
S.No. | Activity | Tasks | Owner | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Drafting the problem statement | Background research | HG, SA, AZ, DG, RO, TK
|  | Talking to stakeholders | HG, SA
|  | Get relevant reports and literature | AZ, DG
|  | Identify measures to evaluate the progress towards goals | TK, RO
2 | Disagrregating the problem | Make preliminary Issue Tree | HG, AZ
|  | Talk to stakeholders | RO, TK
|  | Make changes to the Issue tree, if any | SA,DG
|  | Follow up for any further changes | DG,TK
3 | Data collection | Collect the data | TK, RO
|  | Clean the data for usage | SA, HG
|  | Organise data for usage | TK,SA
|  | Follow up for any further requirement of data | SA
4 | Competition analysis | Identify competititors | TK, DG
|  | Background research | HG, SA
5 | Gap analysis with competitors | Assess Current State of business | TK, RO
|  | Identifying Strengths and Deficiencies | RO, AZ
|  | Identifying Desired State | AZ, HG
|  | Applying Analysis based on measures | SA, HG
6 | Proposal of alternatives | Identification of alternatives | SA, AZ
7 | Evaluation of alternatives | Feasibility Analysis | AZ, HG
|  | Quantitative Analysis | HG, TK
|  | Qualitative Analysis | RO, DG
|  | Expert Feedback | DG,TK
8 | Implementation plan | Choosing best alternative | SA, RO
|  | Refining alternative | RO, AZ
|  | Finalize Suggestion | HG, SA, AZ, DG, RO, TK
|  | Defining responsibilities, requirement,and assumptions | HG
|  | Documentation | TK
9 | Readying deliverables | Preliminary report | AZ
|  | Detailed report | HG, SA, AZ, DG, RO, TK
|  | PPT first draft | HG, SA, AZ, DG, RO, TK
|  | PPT revised draft | HG, SA, AZ, DG, RO, TK