## Deliverables
Task Number | Task Name | Duration (weeks)
Urban Hospital Project
1 | Match IT to organizational task and problem
1.1 | Conduct problem analysis | 4
1.2 | Develop Information on IT technology | 5
2 | Identify IT user needs
2.1 | Interview potential users | 3
2.2 | Develop presentation of IT benefits | 4
2.3 | Gain user "Buy-in" to system
3 | Prepare informal Proposal
3.1 | Develop cost/benefit information | 3
3.2 | gain top management support | 2
4 | Seek and hire IT consultant
4.1 | Delegate members as search committee | 2
4.2 | Develop selection criteria | 3
4.3 | Interview and select consultant
5 | Seek staff and department support for IT | 4
6 | Identify the appropriate location for IT
6.1 | Consult with physical plant engineers | 3
6.2 | Identify possible alternative sites | 4
6.3 | Secure aite approval | 2
7 | Prepare a formal proposal for IT introduction | 3
8 | Solicit RFP's from vendors
8.1 | Develop criteria for decision | 2
8.2 | Contact appropriate vendors | 2
8.3 | Select winners and inform losers | 3
9 | Conduct pilot project | 1
10 | Enter a contarct for purachse | 1
11 | Adopt and use IT technology
11.1 | Initaite employee traininig sessions | 2
11.2 | Develop monitoring system for technical problems | 3

## Resources
Resource Name | Cost/hr
Bob | 100
Sharon | 50
Dave | 80
David | 90
Kent | 60
Ken | 150
James | 200
Susan | 250
Cynthia | 125
Ralph | 260
Terry | 90
Kandra | 40
Beth | 65
Debbie | 130

## Project
Task Number | Task Name | Resources | Cost
| Urban Hospital Project | Bob | 700000
1 | Match IT to organizational task and problem | Sharon | 5000
1.1 | Conduct problem analysis | Sharon | 2500
1.2 | Develop Information on IT technology | Dave | 2500
2 | Identify IT user needs | David | 2750
2.1 | Interview potential users | David | 1000
2.2 | Develop presentation of IT benefits | Kent | 1000
2.3 | Gain user "Buy-in" to system | Ken | 750
3 | Prepare informal Proposal | James | 2000
3.1 | Develop cost/benefit information | James | 2000
3.2 | gain top management support | Bob | 0
4 | Seek and hire IT consultant | Susan | 2500
4.1 | Delegate members as search committee | Susan | 0
4.2 | Develop selection criteria | Susan | 1500
4.3 | Interview and select consultant | Cynthia | 1000
5 | Seek staff and department support for IT | Ralph | 0
6 | Identify the appropriate location for IT | Terry | 1500
6.1 | Consult with physical plant engineers | Kandra | 0
6.2 | Identify possible alternative sites | Terry | 750
6.3 | Secure aite approval | Kandra | 750
7 | Prepare a formal proposal for IT introduction | Bob | 2000
8 | Solicit RFP's from vendors | Beth | 250
8.1 | Develop criteria for decision | Kent | 0
8.2 | Contact appropriate vendors | James | 250
8.3 | Select winners and inform losers | Bob | 0
9 | Conduct pilot project | Debbie | 30000
10 | Enter a contarct for purachse | Bob | 600000
11 | Adopt and use IT technology | David | 54000
11.1 | Initaite employee traininig sessions | David | 30000
11.2 | Develop monitoring system for technical problems | Kandra | 24000